## Feuil1
Probability
VH = 75 - 99 % |  | RATING MATRIX | Probability | 0.9 | VH | G | A | R | R | R
H = 50 - 75 % |  |  |  | 0.6 | H | G | A | A | R | R
M = 35 -50 % |  |  |  | 0.4 | M | G | G | A | A | R
L = 10 - 35 % |  |  |  | 0.25 | L | G | G | A | A | R
VL = 0 - 10 % |  |  |  | 0.1 | VL | G | G | G | A | A
|  | Green < 0.85 |  |  |  | VL | L | M | H | VH
|  | 0.85 <= Amber < 3.6 |  |  |  | 0.5 | 2 | 4 | 8.5 | 16
|  | 3.60 <= Red |  |  |  | Impact
|  | Technical | Schedule |  |  |  |  | Cost
Impact | VL | Min / No Impact | Min / No impact |  |  |  |  | Minimal / No impact
| L | Minor Performance shortfall | Additional activities required, key dates achievable |  |  |  |  | Budget or unit cost increase up to +5%
| M | Moderate shortfall, potential workaround available | Minor slip, required date missed |  |  |  |  | Budget or unit cost increase 5 - 10%
| H | Major shortfall, potential workaround available | Critical Path affected |  |  |  |  | Budget or unit cost increase 10 - 15%
| VH | Unacceptable : Major shortfall, no workaround available | Cannot achieve key milestone(s) |  |  |  |  | Budget or unit cost increase > 15%